## Estimated
On Time
Lately
Early
Unfinished
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17
2,1 | PB2.1 | [AI]Create model AI for create question | 10 | Day 1: 3; Day 2: 3; Day 3: 4
2,2 | PB 2.1 | [AI] Create model AI for predict big5 trait | 10 | Day 1: 3; Day 2: 3; Day 3: 4
2,3 | PB 2.2 | [UI] Design register page app | 4 | Day 4: 4
2,4 | PB2.2 | [DEV] Update user interface register page in app | 14 | Day 5: 3; Day 6: 3; Day 7: 3; Day 8: 3
2,5 | PB2.2 | [DEV] Update API register user | 14 | Day 4: 3; Day 5: 3; Day 6: 3; Day 7: 3; Day 8: 2
2,6 | PB2.2 | [DEV] Update backend in register page app | 6 | Day 9: 3; Day 10: 3
2,7 | PB 2.3 | [TECHNICAL] Research how to collect address of user | 6 | Day 11: 3; Unfinished Day 12: 3
2,8 | PB 2.3 | [DEV]Create API for collect address | 6 | Unfinished Day 13: 3; Unfinished Day 14: 3
2,9 | PB 2.3 | [DEV] Create function for collect address user in app | 9 | Unfinished Day 15: 3; Unfinished Day 16: 3; Unfinished Day 17: 3
|  | Estimated | 0 | 6 | 12 | 20 | 27 | 33 | 39 | 45 | 50 | 53 | 56 | 59 | 62 | 65 | 68 | 71 | 74 | 77

## Actual
SPRINT 1 PLANNING
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19
2,1 | PB2.1 | [AI]Create model AI for create question | 12 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 2
2,2 | PB 2.1 | [AI] Create model AI for predict big5 trait | 12 | Day 1: 3; Day 2: 3; Day 3: 3; Day 4: 2 | `
2,3 | PB 2.2 | [UI] Design register page app | 4 | Day 5: 4
2,4 | PB2.2 | [DEV] Update user interface register page in app | 9 | Day 6: 3; Day 7: 3; Day 8: 3
2,5 | PB2.2 | [DEV] Update API register user | 12 | Day 5: 3; Day 6: 3; Day 7: 3; Day 8: 3
2,6 | PB2.2 | [DEV] Update backend in register page app | 6 | Day 9: 3; Day 10: 3
2,7 | PB 2.3 | [TECHNICAL] Research how to collect address of user | 9 | Day 11: 3; Day 12: 3; Day 13: 3
2,8 | PB 2.3 | [DEV]Create API for collect address | 9 | Day 14: 3; Day 15: 3; Day 16: 3
2,9 | PB 2.3 | [DEV] Create function for collect address user in app | 9 | Day 17: 3; Day 18: 3; Day 19: 3
|  | Actual | 0 | 6 | 12 | 18 | 22 | 29 | 35 | 41 | 47 | 50 | 53 | 56 | 59 | 62 | 65 | 68 | 71 | 74 | 77 | 80