## Estimated
Team Availibility
|  | Name |  | Available Hours | Estimation Total
|  | Hieu, Nguyen Trung |  | 0 | 0
|  | Quoc, Nguyen Anh |  | 0
|  | Tuong, Hien Duong |  | 0
|  | Anh, Nguyen Quoc |  | 0
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11
4,1 | PB 4.1 | [UI] Design UI for create question from keywords connect big5 indicator trait | 3 | 0 Day 1: 3
4,2 | PB 4.1 | [DEV]Code UI for create question from keywords connect big5 indicator trait | 3 | 0 Day 2: 3
4,3 | PB 4.1 | [DEV] Code function for create question from keywords connect big5 indicator trait | 3 | 0 Day 3: 1; 0 Day 4: 2
4,4 | PB 4.2 | [UI] Design UI for save and send question to all user | 3 | 0 Day 5: 3
4,5 | PB 4.2 | [DEV] Code API send question to all user | 6 | 0 Day 6: 3
4,6 | PB 4.2 | [DEV] Code UI for save and send question to all user | 3 | 0 Day 7: 3
4,7 | PB 4.2 | [DEV] Code function for save and send question | 3 | 0 Day 7: 2; 0 Day 8: 1
4,8 | PB 4.3 | [UI] Design UI notification | 3 | 0 Day 9: 3
4,9 | PB 4.3 | [DEV] Code UI notification | 3 | 0 Day 10: 3
4,10 | PB 4.3 | [DEV] Code function notification1 | 3 | 0 Day 11: 3
|  | Estimated | 0 | 3 | 6 | 7 | 9 | 12 | 15 | 20 | 21 | 24 | 27 | 30

## Actual
SPRINT 1 PLANNING
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11
4,1 | PB 4.1 | [UI] Design UI for create question from keywords connect big5 indicator trait | 3 | Day 1: 3
4,2 | PB 4.1 | [DEV]Code UI for create question from keywords connect big5 indicator trait | 3 | Day 2: 3
4,3 | PB 4.1 | [DEV] Code function for create question from keywords connect big5 indicator trait | 3 | Day 3: 1; Day 4: 2
4,4 | PB 4.2 | [UI] Design UI for save and send question to all user | 3 | Day 5: 3
4,5 | PB 4.2 | [DEV] Code API send question to all user | 3 | Day 6: 3
4,6 | PB 4.2 | [DEV] Code UI for save and send question to all user | 2 | Day 7: 2
4,7 | PB 4.2 | [DEV] Code function for save and send question | 3 | Day 7: 2; Day 8: 1 | `
4,8 | PB 4.3 | [UI] Design UI notification | 2 | Day 9: 2
4,9 | PB 4.3 | [DEV] Code UI notification | 2 | Day 10: 2
4,10 | PB 4.3 | [DEV] Code function notification1 | 3 | Day 11: 3
|  | Actual | 0 | 3 | 6 | 7 | 9 | 12 | 15 | 19 | 20 | 22 | 24 | 27