## Main
Scrum Project |  |  | Product Status
Sponsor
Product | GB5 |  | Product Owner | Chung, Bao Hoang
Active versions | v1.4 |  | Project Champion
Team |  |  | Other Stakeholders | Doctor. Habil. Binh, Thanh Nguyen
Scrum Master | Chinh, Huu Thai
Developers | Chung, Bao Hoang
Loc, Tien Nguyen
Hau, Phuc Bui
Projects
Id | Description | Start | End | Status | Remarks
1 | Initial release | 2021-08-15 | 2021-08-22 | Complete
2021-01-01 | Project’s Kick-off Meeting | 2021-08-15 | 2021-08-16 | Complete
2021-02-01 | Collect and analyse requirements | 2021-08-16 | 2021-08-17 | Complete
2021-03-01 | Setup Development Environment | 2021-08-18 | 2021-08-19 | Complete
2021-03-01 | Research Technical | 2021-08-20 | 2021-08-21 | In Progress
2 | Develop | 2021-08-23 | 15/ thg 12/21
2021-01-02 | Srpint 1 | 2021-08-23 | 2021-09-22 | Complete
2021-02-02 | Srpint 2 | 2021-09-22 | 2021-10-20 | In Progress
2021-03-02 | Srpint 3 | 2021-10-23 | 23-thg 11-21 | In Progress
2021-04-02 | Sprint 4 | 24-thg 11-21 | 15-thg 12-21 | Complete
Sprint Plan
Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
Spr. 1.1 | 2021-08-15 | 2021-08-16 | Complete | 3 | 3
Spr. 1.2 | 2021-08-16 | 2021-08-17 | Complete | 13 | 13
Spr. 1.3 | 2021-08-18 | 2021-08-19 | Complete | 21 | 20
Spr. 1.4 | 2021-08-20 | 2021-08-21 | In Progress | 55 | 50
Spr.2.1 | 2021-08-23 | 2021-09-22 | Complete | 144 | 140
Spr 2.2 | 2021-09-22 | 2021-10-20 | In Progress | 89 | 83
Spr 2.3 | 2021-10-23 | 23-thg 11-21 | In Progress | 92 | 81
Spr 2.4 | 24-thg 11-21 | 15-thg 12-21 | Complete | 84 | 84

## Backlog
Backlog
Id | Epics | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
Sprint 1 | [6 empty] | M
PB1.1 | Login on GB5 application | User | The User wants to log in to the system with their account. | Log in to the system with their account. | Minimum password length 8 characters maximum 50 characters. Enter the correct phone number and password, then I can log into the system. Enter the wrong phone number or password or both of me can not login to the system. I entered wrong phone number or password, I want to be told exactly what I am wrong |  | L
PB1.2 | Register on GB5 application | User | I want to register for an account to log into the system | Register for an account to log into the system to use the feature of the app | Minimum password length 8 characters maximum 50 characters. The user enter missing information will be notified exactly what I am missing |  | L
PB1.3 | Logout GB5 application | User | I want when I press the logout button I will exit the system | When they press the logout button, they will exit the system | The tourist press the logout button, I will exit the system and return Home Screen. Displays a message when you cannot log out |  | L
PB1.4 | Receive notìication | User | I want to know when the new question arrive | Would know the new question have arrived yet | Notify to the user in a specific time-line |  | L
Sprint 2
PB 2.1 | View Question | User | I want to see the question | See the question sent by the Administrator/ Content manager | Users can see the question after login/ Sign In into the App. User can see after the question send a notification to them |  | M
PB 2.2 | Answer Question | User | I want to Answer the question | Answer the question in the app/ sent by administrator/ Content Manager | Display below the question. Not require to choose but highly recommend |  | H
PB 2.3 | View Information | User | I see my own information | See their own information | See all information : Phone number, user name, full name |  | L
PB 2.4 | Modifying user information | User | I want to change my information | Change their information | Changeable: User name, Phone number, Full name,. Recommended attractions for users |  | L
PB 2.5 | Login to the Dashboard | As an administrator/ Content manager | I want to access the system with my account so that when I enter the Account and password into the [Account] field, the [Password] field and then I click the login button and I can use the system. | Can login to the dashboard | Provided & Changeable |  | M
Sprint 3
PB 3.1 | Logout to the Dashboard | As an administrator/ Content manager | I can logout the dashboard | Logout the dashboard | Confirm if the user want to logout |  | M
PB 3.2 | Visualize to the user data | As an administrator/ Content manager | I can see the user data in a table… | can see the user data | Each user column links to use information details such as phone number…….Show each trait point |  | M
PB 3.3 | Edit question in the dashboard | As an administrator/ Content manager | I can edit the question data in a table… | can edit the user trait data |  |  | H
PB 3.4 | View question in the dashboard | As an administrator/ Content manager | I can see the question data in a table… | can see the user trait data | When clicking the check-box in front of the question, the website shows the indicator, trait level. |  | H
Sprint 4
PB 4.1 | Send question to the user | As an administrator/ Content manager | Send the question to the specific user team | Can find the user's trait clearly |  |  | H
PB 4.2 | Create question in the dashboard | As an administrator/ Content manager | Create the question data in a table… | can create the user trait data |  |  | H
PB 4.3 | Delete question in the dashboard | As an administrator/ Content manager | Delete the question data in a table… | can delete the user trait data |  |  | M
PB 4.4 | Visualize all trait data | As an administrator/ Content manager | See the trait data in a chart… | can see the user trait data | When clicking the check-box in front of the question, the website shows the indicator, trait level. |  | M
PB 4.5 | Input indicator | As an administrator/ Content manager | Input the indicator into the database | I can input the indicator into the database |  |  | H

## Sprint 1 Task
Sprint Task 1
<- effort / day ->
Sprint Id | Backlog Id | Sprint Id | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
1,1 | PB1.1 | [UI] Login Screen | Hau | Done | 3 | 3 | 0 | 2 | 1
1,2 | PB1.2 | [UI] Sign Out Screen | Hau | Done | 3 | 3 | 0 | 1 | 2
1,3 | PB1.3 | [UI] Register Screen | Chinh | Done | 3 | 3 | 0 |  |  |  |  | 2 |  |  | 1
1,4 | PB1.1 | [DEV] Login Screen | Chung | Done | 2 | 2 | 0 |  |  |  |  | 1 | 1
1,5 | PB1.2 | [DEV] Sign Out Screen | Loc | Done | 5 | 5 | 0 | [5 empty] | 2 | 3
1,6 | PB1.3 | [DEV] Register Screen | Chung | Done | 5 | 5 | 0 | [10 empty] | 1 | 1 | 2 | 1
1,7 |  | [DB] Design Database | Loc | Done | 8 | 8 | 0 | 1 | 1 | 2 | 2 | [20 empty] | 2
1,8 | PB1.4 | [DEV] Receive notìication | Loc |  | 3 | 3 | 0 |  |  | 1 | 1 | 1
1,9 | PB 2.1 | [UI] Question Screen | Chinh | Done | 2 | 2 | 0 | [10 empty] | 1 | 1
1,10 | PB 2.1 | [DEV] Develop question Screen | Chung,Loc | Done | 34 | 34 | 0 |  | 3 |  | 2 |  |  |  |  | 2 | 2 | 2 | 2 |  |  | 2 | 2 |  |  |  | 1 | 2 | 2 | 3 | 2 | 1 | 1 | 3 | 2
1,11 | PB1.1 | [DEV] Develop login Screen | Hau | Done | 8 | 6 | 2 | [16 empty] | 1 |  |  | 1 | 1 | 1 |  |  |  | 1 | 1
1,12 |  | [DEV] Develop Question Database | Loc | Done | 21 | 21 | 0 | 3 | 1 | 1 | 2 | 2 | [11 empty] | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1
1,13 |  | [DEV] Develop User Database | Loc |  | 21 | 18 | 3 |  |  |  | . | [14 empty] | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1,14 | PB1.2 | [TEST] Testing Sign Out Screen | All member | Done | 2 | 2 | 0 | [13 empty] | 1 | [11 empty] | 1
1,15 | PB1.1 | [TEST] Testing Sign In Screen | All member | Done | 5 | 5 | 0 | [5 empty] | 2 | [7 empty] | 3
1,16 | PB1.3 | [TEST] Testing Register Screen | All member | Done | 5 | 5 | 0 | [12 empty] | 5
1,17 | PB 2.1 | [TEST] Tesing Question Screen | All member | Done | 5 | 5 | 0 | [13 empty] | 2 | [11 empty] | 3
1,18 |  | Proposal | Chinh | Done | 2 | 2 | 0 | [7 empty] | 1 | 1
1,19 |  | Project Plan | All member | Done | 2 | 2 | 0 | [15 empty] | 1 |  | 1
1,20 |  | Architecture Document | All member | Done | 3 | 3 | 0 | [7 empty] | 1 | [7 empty] | 1 |  | 1
1,21 |  | Interface Desgin | All member | Done | 1 | 1 | 0 | [9 empty] | 1
1.22 |  | Test plan creating | All member | Done | 2 | 1 | 1 | [18 empty] | 1
|  |  |  | Total | 145 | 139 | 6 | 7 | 8 | 4 | 7 | 6 | 5 | 3 | 3 | 3 | 3 | 4 | 4 | 7 | 7 | 2 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 5 | 5 | 8 | 6 | 4
|  |  |  | Burn down |  |  |  | 138 | 130 | 126 | 119 | 113 | 108 | 105 | 102 | 99 | 96 | 92 | 88 | 81 | 74 | 72 | 68 | 64 | 60 | 56 | 52 | 46 | 40 | 34 | 29 | 24 | 16 | 10 | 6
|  |  |  | Burn up |  |  |  | 7 | 15 | 19 | 26 | 32 | 37 | 40 | 43 | 46 | 49 | 53 | 57 | 64 | 71 | 73 | 77 | 81 | 85 | 89 | 93 | 99 | 105 | 111 | 116 | 121 | 129 | 135 | 139
0

## Sprint 2 Task
Sprint Task 2
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48
2,1 |  | Colecting Big-five Indicator | Chinh |  | 21 | 17 | 4 | [10 empty] | 2 | 3 | 2 |  |  |  | 3 | 3 | 3 | 1
2,2 | PB 2.3 | [UI] Design User info Screen | Hau | Done | 3 | 3 | 0 |  | 2 | 1
2,3 | PB 2.1 | [DEV] Develop View Question | Chung | Done | 13 | 13 | 0 | [9 empty] | 1 | 1 |  | 1 | 1 | 2 |  | 1 | 2 | 2 | 2
2,4 |  | [DEV] Develop User Database | Loc | Done | 13 | 13 | 0 | 1 |  |  | 1 | 1 |  | 2 | 2 | 4 |  | 1 |  |  |  |  | 1
2,5 | PB 2.1, 2.2 | [UI] Design Question Screen | Hau | Done | 5 | 5 | 0 |  |  |  | 1 |  | 1 | 1 | 1 |  | 1
2,6 |  | [TEST] Test GB5 Application | All member | Done | 8 | 8 | 0 |  | 1 | 1 | [6 empty] | 1 |  | 2 | 1 |  |  |  |  | 1 |  | 1
2,7 | PB 2.3 | [UI] Design User Page | Hau | Done | 2 | 2 | 0 | [5 empty] | 1 |  | 1
2,8 | PB 2.3 | [UI] Login to the Dashboard UI | Hau | Done | 3 | 3 | 0 | 1 |  |  | 1 | 1
2,9 | PB 2.4 | [DEV] Develop user infomation screen | Loc |  | 2 | 1 | 1 | 1
2,10 | PB 2.2 | [DEV] Develop Answer Question | Chung | Done | 2 | 2 | 0 | [17 empty] | 1 | 1
2,11 | PB 2.5 | [UI] Design Login to the Dashboard | Hau | Done | 3 | 3 | 0 | [13 empty] | 1 | 1 | 1
2,12 |  | Architecture Document Creating | Chung | Done | 5 | 5 | 0 |  | 1 |  | 1 | 1 | 2
2,13 |  | Database Design Creating | Loc | Done | 8 | 3 | 5 |  |  | 1 | [6 empty] | 1 |  |  |  | 1
2,14 |  | Test plan creating | All member | Done | 1 | 1 | 0 | [15 empty] | 1
2,15 |  |  |  |  | 0 | 0 | 0
2,16 |  |  |  |  | 0 | 0 | 0
|  |  |  | Total | 89 | 79 | 10 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 4 | 5 | 4 | 3 | 3 | 3 | 4 | 7 | 6 | 4
|  |  |  | Burn down |  |  |  | 86 | 82 | 79 | 75 | 72 | 68 | 65 | 61 | 57 | 53 | 49 | 44 | 40 | 37 | 34 | 31 | 27 | 20 | 14 | 10
|  |  |  | Burn up |  |  |  | 3 | 7 | 10 | 14 | 17 | 21 | 24 | 28 | 32 | 36 | 40 | 45 | 49 | 52 | 55 | 58 | 62 | 69 | 75 | 79

## Sprint 3 Task
Sprint Task 3
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 50 | Day 51 | Day 52 | Day 53 | Day 54 | Day 55 | Day 56 | Day 57 | Day 58 | Day 59 | Day 60 | Day 61 | Day 62 | Day 63 | Day 64 | Day 65 | Day 66 | Day 67 | Day 68 | Day 69 | Day 70 | Day 71 | Day 72 | Day 73 | Day 74 | Day 75 | Day 76 | Day 77
3,1 | PB 3.1 | [UI] Design Logout the Dashboard | Hau | Done | 8 | 8 | 0 | 1 | 2 | 1 | 1 | 2 |  |  |  | 1
3,2 | PB 3.2 | [DEV] Develop Logout the Dashboard | Hau | Done | 13 | 13 | 0 | [7 empty] | 2 |  | 2 |  | 1 | 2 | 1 | 1 |  | 2 |  | 2
3,3 | PB 3.3 | [UI] Design User Page | Chinh | Done | 8 | 8 | 0 | 1 |  | 1 | 1 |  |  |  |  | 2 |  |  | 2 | 1
3,4 | PB 2,5 | [DEV] Develop Login the Dashbord | Loc | Done | 3 | 0 | 3
3,5 | PB 2,5 | [TEST] Test Login the Dashboard | Chung | Done | 2 | 0 | 2
3,6 | PB 3.3 | [DEV] User Page | Chung |  | 13 | 8 | 5 | [17 empty] | 2 |  | 1 | 1 |  |  | 1 | 2 |  | 1
3,7 | PB 3.3 | [DEV] User table | Chung | Done | 13 | 11 | 2 | [16 empty] | 3 |  | 1 |  |  | 1 |  | 2 |  | 1 | 1 | 2
3,8 |  | [DEV] Develop select team automatic | Loc | Done | 13 | 13 | 0 | [10 empty] | 1 |  |  |  |  | 3 |  | 1 |  | 2 | 1 | 1 | 1 |  |  | 1 |  | 2
3,9 | PB 3.5 | [DEV] View question in the dashboard | Loc | Done | 8 | 8 | 0 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 2 |  |  | 1
3,10 | PB 3.5 | [UI] Design View question | Hau | Done | 5 | 5 | 0 |  | 2 |  |  | 1 | 2
3,11 |  | Colecting Big-five Indicator | Chinh | Done | 3 | 4 | -1 | 1 |  | 1 | 1 |  | 1
3,12 |  | Test case document | All member | Done | 3 | 3 | 0 | [13 empty] | 1 | 1 | [11 empty] | 1
|  |  |  | Total | 92 | 81 | 11 | 3 | 4 | 3 | 3 | 3 | 3 | 0 | 2 | 3 | 2 | 1 | 3 | 3 | 2 | 2 | 3 | 5 | 3 | 3 | 4 | 3 | 3 | 2 | 4 | 4 | 2 | 3 | 5
|  |  |  | Burn down |  |  |  | 89 | 85 | 82 | 79 | 76 | 73 | 73 | 71 | 68 | 66 | 65 | 62 | 59 | 57 | 55 | 52 | 47 | 44 | 41 | 37 | 34 | 31 | 29 | 25 | 21 | 19 | 16 | 11
|  |  |  | Burn up |  |  |  | 3 | 7 | 10 | 13 | 16 | 19 | 19 | 21 | 24 | 26 | 27 | 30 | 33 | 35 | 37 | 40 | 45 | 48 | 51 | 55 | 58 | 61 | 63 | 67 | 71 | 73 | 76 | 81

## Sprint 4 Task
Sprint Task 4
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 78 | Day 79 | Day 80 | Day 81 | Day 82 | Day 83 | Day 84 | Day 85 | Day 86 | Day 87 | Day 88 | Day 89 | Day 90 | Day 91 | Day 92 | Day 93 | Day 94 | Day 95 | Day 96 | Day 97 | Day 98 | Day 99 | Day 100 | Day 101 | Day 102 | Day 103 | Day 104 | Day 105
4,1 | PB 4.1 | [UI] Question Page | Hau | Done | 5 | 5 | 0 | 1 | 2 | 2
4,2 | PB 4.2 | [DEV] Create question in the dashboard | Loc | Done | 8 | 8 | 0 |  |  | 1 |  |  | 2 | 2 | 1 | 1 | 1
4,3 | PB 4.3 | [UI] Design Delete question in the dashboard | Chinh | Done | 3 | 3 | 0 |  | 1 |  | 1 | 1
4,4 | PB 4.4 | [DEV] Visualize all trait data | Chung | Done | 2 | 2 | 0 | [22 empty] | 1 | 1
4,5 | PB 4.1 | [DEV] Send question to the user | Hau,Loc | Done | 21 | 21 | 0 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
4,6 | PB 4.4 | [DEV] Dashboard Page | Hau,Loc | Done | 13 | 13 | 0 | [7 empty] | 1 | 1 | 2 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
4,7 | PB 4.3 | [UI] Design Delete question in the dashboard | Hau | Done | 1 | 1 | 0 |  |  |  | 1
4,8 | PB 4.5 | [DEV] Develop Input Indicator | Chinh | Done | 2 | 2 | 0 |  |  | 1 |  | 1
4,9 | PB 3.3 | [TEST] Test user Page | All member | Done | 2 | 2 | 0 | [23 empty] | 1 |  |  | 1
4,10 | PB 4.1 | [TEST] Send question to user | All member | Done | 8 | 8 | 0 | [23 empty] | 2 | 2 | 2 | 1 | 1
4,11 |  | Team Reflection | All member | Done | 5 | 5 | 0 | [5 empty] | 1 | 1 | [10 empty] | 2 | 1
4,12 |  | Team meeting document | All member | Done | 3 | 3 | 0 | [19 empty] | 1 |  |  |  |  | 2
4,13 |  | Mentor meeting document | All member | Done | 3 | 3 | 0 | [21 empty] | 1 |  |  |  | 2
4,14 | PB 3.3 | [DEV] User Page | Chung | Done | 8 | 8 | 0 |  |  |  | 1 | 1 |  |  | 2 | 2 | [17 empty] | 1 | 1
|  |  |  | Total | 84 | 84 | 0 | 1 | 3 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 3 | 3 | 2 | 2 | 2 | 5 | 5 | 5 | 4 | 4
|  |  |  | Burn down |  |  |  | 83 | 80 | 76 | 73 | 70 | 67 | 64 | 60 | 56 | 53 | 51 | 49 | 47 | 45 | 43 | 41 | 39 | 35 | 32 | 29 | 27 | 25 | 23 | 18 | 13 | 8 | 4 | 0
|  |  |  | Burn up |  |  |  | 1 | 4 | 8 | 11 | 14 | 17 | 20 | 24 | 28 | 31 | 33 | 35 | 37 | 39 | 41 | 43 | 45 | 49 | 52 | 55 | 57 | 59 | 61 | 66 | 71 | 76 | 80 | 84

## Impediment
Impediments |  | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks
Id | Description
1 | Weak network connection | Network providers |  | 4 |  | Network providers |  | Invest heavily in network, bandwidth and transmission lines, use multiple modems
2 | High investment money | Loc |  | 1 |  | Loc |  | Give a detailed plan, be careful in calculating wages and supporting equipment
3 | Difficult technique causes many obstacles | Hau |  | 1 |  | Hau |  | Train skilled software engineers or hire experienced people
4 | Entering data into the software is difficult and time consuming | Chung |  | 2 |  | Chung
5 | There are high costs incurred in the implementation process | Chinh |  | 1 |  | Chinh
6 | Human problems: sickness, resignation, personal problem ... | Chinh |  | 1 |  | Chinh
7 | Natural disasters: storms, floods, .. | All member |  | 1 |  | All member
8 | Database disconnection | All member |  | 4 |  | All member |  | Avoid the server back-up time

## Retrospective
Retrospective Log |  |  |  | Start Doing | Stop Doing | Remarks
Sprint # | Date | Owner | Continue Doing
1 | 2021-10-10 | Chinh |  |  | Develop Chatbox
2 | 2021-10-21 | Chung, Loc |  |  | Develop Ranking

## Summary
Reports & Dashboards
Sprint Velocity
Sprint 1
Sprint 2
Sprint 3
Sprint 4

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms