## Estimated
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33
1,1 | PB1.1 | [CONTENT] Research what is big5 model through document | 4 | Day 1: 2; Day 2: 2
1,2 | PB1.1 | [CONTENT]Research why is big5 model can relation to envieronment | 2 | Day 3: 2
1,3 | PB1.2 | [DOCUMENT]Research all doc of the project | 4 | Day 4: 2; Day 5: 2
1,4 | PB1.2 | [TECHNICAL]Research technical use for app | 10 | Day 6: 2; Day 7: 2; Day 8: 2; Day 9: 2; Day 10: 2
1,5 | PB1.2 | [TECHNICAL]Research technical use for website | 10 | Day 6: 2; Day 7: 2; Day 8: 2; Day 9: 2; Day 10: 2
1,6 | PB1.2 | [SOURCE]Research source code for app | 8 | Day 11: 2; Day 12: 2; Day 13: 2; Day 14: 2
1,7 | PB1.2 | [SOURCE]Research source code for website | 6 | Day 11: 2; Day 12: 2; Day 13: 2
1,8 | PB1.3 | [CONTENT]Research indicator of big5 trait | 3 | Day 15: 3
1,9 | PB1.3 | [CONTENT]Find keywords for environment | 4 | Day 16: 2; Day 17: 2
1,10 | PB1.3 | [CONTENT]Research how to create question from keywords connect big5 indicator trait | 4 | Day 18: 2; Day 19: 2
1,11 | PB1.3 | [CONTENT] Find the paragraps from the keywords connect big5 indicator trait have mean | 8 | Day 20: 2; Day 21: 2; Day 22: 2; Day 23: 2
1,13 | PB1.4 | [TECHNICAL]Research model AI to predict big5 trait | 10 | Day 24: 2; Day 25: 2; Day 26: 2; Day 27: 2; Day 28: 2
1,14 | PB1.4 | [TECHNICAL]Research model AI to create question from keywords connect big5 indicator trait | 10 | Day 29: 2; Day 30: 2; Day 31: 2; Day 32: 2; Day 33: 2
|  | Estimated | 0 | 2 | 4 | 6 | 8 | 10 | 14 | 18 | 22 | 26 | 30 | 34 | 38 | 42 | 44 | 47 | 49 | 51 | 53 | 55 | 57 | 59 | 61 | 63 | 65 | 67 | 69 | 71 | 73 | 75 | 77 | 79 | 81 | 83

## Actual
SPRINT 1 PLANNING
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39
1,1 | PB1.1 | [CONTENT] Research what is big5 model through document | 4 | Day 1: 2; Day 2: 2
1,2 | PB1.1 | [CONTENT]Research why is big5 model can relation to envieronment | 2 | Day 3: 2
1,3 | PB1.2 | [DOCUMENT]Research all doc of the project | 4 | Day 4: 2; Day 5: 2 | `
1,4 | PB1.2 | [TECHNICAL]Research technical use for app | 14 | Day 6: 2; Day 7: 2; Day 8: 2; Day 9: 2; Day 10: 2; Day 11: 2; Day 12: 2
1,5 | PB1.2 | [TECHNICAL]Research technical use for website | 10 | Day 6: 2; Day 7: 2; Day 8: 2; Day 9: 2; Day 10: 2
1,6 | PB1.2 | [SOURCE]Research source code for app | 8 | Day 13: 2; Day 14: 2; Day 15: 2; Day 16: 2
1,7 | PB1.2 | [SOURCE]Research source code for website | 6 | Day 11: 2; Day 12: 2; Day 13: 2
1,8 | PB1.3 | [CONTENT]Research indicator of big5 trait | 3 | Day 17: 3
1,9 | PB1.3 | [CONTENT]Find keywords for environment | 4 | Day 18: 2; Day 19: 2
1,10 | PB1.3 | [CONTENT]Research how to create question from keywords connect big5 indicator trait | 6 | Day 20: 2; Day 21: 2; Day 22: 2
1,11 | PB1.3 | [CONTENT] Find the paragraps from the keywords connect big5 indicator trait have mean | 10 | Day 23: 2; Day 24: 2; Day 25: 2; Day 26: 2; Day 27: 2
1,13 | PB1.4 | [TECHNICAL]Research model AI to predict big5 trait | 12 | Day 28: 2; Day 29: 2; Day 30: 2; Day 31: 2; Day 32: 2; Day 33: 2
1,14 | PB1.4 | [TECHNICAL]Research model AI to create question from keywords connect big5 indicator trait | 12 | Day 34: 2; Day 35: 2; Day 36: 2; Day 37: 2; Day 38: 2; Day 39: 2
|  | Actual | 0 | 2 | 4 | 6 | 8 | 10 | 14 | 18 | 22 | 26 | 30 | 34 | 38 | 42 | 44 | 46 | 48 | 51 | 53 | 55 | 57 | 59 | 61 | 63 | 65 | 67 | 69 | 71 | 73 | 75 | 77 | 79 | 81 | 83 | 85 | 87 | 89 | 91 | 93 | 95