## Estimated
Team Availibility
|  | Name |  | Available Hours | Estimation Total
|  | Hieu, Nguyen Trung |  | 0 | 0
|  | Quoc, Nguyen Anh |  | 0
|  | Tuong, Hien Duong |  | 0
|  | Anh, Nguyen Quoc |  | 0
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
3,1 | PB 3.1 | [TECHNICAL] Research how to create API of python | 3 | 0 Day 1: 3
3,2 | PB 3.1 | [DEV]Write API to use model | 3 | 0 Day 2: 3
3,3 | PB 3.2 | [UI]Create API for get keywords | 3 | 0 Day 3: 3
3,4 | PB 3.2 | [UI]Design UI for connect keywords and big5 indicator trait | 3 | 0 Day 4: 3
3,5 | PB 3.2 | [DEV] Code UI for connect keywords and big5 indicator trait | 6 | 0 Day 5: 3; 0 Day 6: 3
3,6 | PB 3.2 | [DEV] Code function for connect keywords and big5 indicator trait | 24 | 0 Day 7: 3; 0 Day 8: 3; 0 Day 9: 3; 0 Day 10: 3; 0 Day 11: 3; 0 Day 12: 3; 0 Day 13: 3; 0 Day 14: 3
|  | Estimated | 0 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42

## Actual
SPRINT 1 PLANNING
Sprint Id | Backlog Id | Task name | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
3,1 | PB 3.1 | [TECHNICAL] Research how to create API of python | 3 | Day 1: 3
3,2 | PB 3.1 | [DEV]Write API to use model | 3 | Day 2: 3
3,3 | PB 3.2 | [UI]Create API for get keywords | 3 | Day 3: 3
3,4 | PB 3.2 | [UI]Design UI for connect keywords and big5 indicator trait | 6 | Day 4: 2; Day 5: 4
3,5 | PB 3.2 | [DEV] Code UI for connect keywords and big5 indicator trait | 6 | Day 6: 4; Day 7: 2
3,6 | PB 3.2 | [DEV] Code function for connect keywords and big5 indicator trait | 24 | Day 8: 3; Day 9: 2; Day 10: 4; Day 11: 2; Day 12: 2; Day 13: 5; Day 14: 3 | `
|  | Actual | 0 | 3 | 6 | 9 | 11 | 15 | 19 | 21 | 24 | 26 | 30 | 32 | 34 | 39 | 42