## Main
Scrum Project
|  | Product | GB5
|  | Active versions | v2.3
Team
|  | Scrum Master | Chung,Hoang Bao
|  | Developers | Loc, Nguyen Tien
Vinh, Do Quang
Kha,Ngo Van
Product Status
Sponsor
|  | Product Owner | Loc, Nguyen Tien
Project Champion
|  | Other Stakeholders | Doctor. Habil. Binh, Thanh Nguyen
Projects
Id | Description | Start | End | Status | Remarks
1 | Initial release | 2022-02-18 | 2021-02-20 | Complete
1.1 | Project’s Kick-off Meeting | 2022-02-18 | 2022-02-19 | Complete
1.2 | Collect and analyse requirements | 2022-02-20 | 2022-02-22 | Complete
1.3 | Setup Development Environment | 2022-02-22 | 2022-02-23 | Complete
1.4 | Research Technical | 2022-02-23 | 2022-04-04 | Complete
2 | Develop | 2022-03-01 | 2022-05-16
2021-01-02 | Srpint 1 | 2022-03-01 | 2022-04-04 | Complete
2021-02-02 | Srpint 2 | 2022-04-04 | 2022-04-23 | Complete
2021-03-02 | Srpint 3 | 2022-04-23 | 2022-05-06 | Complete
2.4 | Sprint 4 | 2022-05-06 | 2022-05-16 | Complete

## Backlog
Backlog
Id | Epics | As a.. | I want to .. | so that ..
Sprint 1
PB1.1 | Research big5 personality model | Developer | Understand the project | Reseach about big5 personality model through internet or document
PB1.2 | Research about the project | Developer | Understand about technical and requirement for project | Research document and technical for the project
PB1.3 | Find content about keywords of environtment and big5 indicator trait | Developer | Understand about connect about big5 indicator trait and keywords of environment | Find keywords for environent and research about big5 indicator trait
PB1.4 | Research model AI for create question from keyword connect big5 indicator trait,modelAI for predict big5 trait | Developer | Understand about auto create question from keywords connect big5 indicator trait,auto predict big5 trait | Reseach model AI
Sprint 2
PB 2.1 | Create model AI for create question and predict big5 trait | Developer | Create question and predict big5 trait | Create model AI
PB 2.2 | Update register page in app | Developer | Update register page to concide with new major | Update code
PB 2.3 | Collect address of user | Developer | Collect address of user | Create function for get address
Sprint 3
PB 3.1 | Create API for function python | As a developer | Use API python for run function(model AI) in python | Create API from python
PB 3.2 | Connect keywords and big5 indicator trait become a tree | As an administrator/ Content manager | Create keywords connect big5 indicator trait become a tree | Can see relationship about keywords and big5 indicator trait
Sprint 4
PB 4.1 | Create question from keywords connect big5 indicator trait | As an administrator/ Content manager | Create the question | Can have new question
PB 4.2 | Save or send question | As an administrator/ Content manager | Save or send question to all user | Can get more data for question or user
PB 4.3 | Notification flow of model AI and the staus of question | As an administrator/ Content manager | See the flow of model AI for question and the status question was send | Can see the rightness